SeamFlow

Where tailors and the people they dress meet

Marketing & Content Strategy — v2

Facebook + Instagram (+ WhatsApp Status)

Tailors & fashion designers  +  their clients · Douala, Cameroon · English + French · 2-month plan

Pre-launch phase — build both audiences before the video ads

September 2026 · Replaces the tailor-only plan (August 2026)

# How to use this document

This is the updated playbook for the next two months on Facebook and Instagram, before the video ads start. The first plan was written when SeamFlow was a workshop tool for tailors only. SeamFlow is now one app with two sides: a workshop for tailors and fashion designers, and a place where clients find a tailor, show what they want made, and follow their order. This plan speaks to both.

The goal for this phase stays the same: build a warm, credible page with real content, so that when the ads go live, anyone who clicks through, tailor or client, lands on a page that already looks alive and trustworthy.

One rule above all: we are not selling an app. We are bringing together people who want beautiful clothes made for them and the tailors who make them, and taking the stress out of everything in between. Every post should make a tailor feel "this brings me work and makes my life easier", or make a client feel "this is how I find my tailor and get what I actually want."

Phase settings for this plan: audience = tailors & fashion designers (solo and growing ateliers) and their clients; language = English + French; call-to-action = soft ("follow / coming soon to Douala"), no public sign-up push yet; content = designed graphics, app screenshots, and real work from founding tailors (with their permission).

# 0. What changed since the first plan

| Area | First plan (Aug 2026) | This plan (Sep 2026) |
| --- | --- | --- |
| Who it is for | Tailors only | Tailors & fashion designers and their clients |
| What SeamFlow is | A workshop organiser | A workshop organiser plus a place to discover tailors, request a piece, chat and track orders |
| Big idea | "The calm, organised workshop" | "Two sides, one thread": the tailor and the client meet, and the whole order runs calmly in one place |
| Content pillars | 5 pillars, all tailor-facing | 6 pillars, tagged Tailor / Client / Both |
| Growth engine | Page followers | Founding tailors publish real work first, then clients come for that work (new section 8) |
| Brand colours | Indigo #2E3A8C + copper #C97B5C | Current brand purple #7B30E8 / violet #5A18C9 + copper #D9673D (matches the flyers and the app) |
| Bio, highlights, hashtags | Tailor wording | Rewritten for both audiences |
| What to measure | Page growth | Page growth split by audience, plus founding tailors and published pieces |

What stays the same: pre-launch with a soft call-to-action, Douala first, English + French, Facebook + Instagram with WhatsApp Status as the multiplier, 4 feed posts a week, and the warm, calm, crafted voice.

# 1. What SeamFlow is right now

One app, one account. When someone signs up, SeamFlow asks "What brings you to SeamFlow?": "I'm a tailor" or "I want to find a tailor." Each person gets the experience made for them, and anyone can switch sides at any time (a tailor can "Browse as a customer", a client can "Set up your shop"). Clients can browse without an account; they only sign in to act.

## What each side can do today

| For tailors & fashion designers | For clients |
| --- | --- |
| Clients & measurements: save every client once, reuse their sizes, build your own measurement templates | Discover: a feed of real finished work by real tailors, filtered by women / men / children and by occasion (wedding, traditional, corporate, casual, party) |
| Scan a paper measurement sheet with the camera and the numbers fill in | Tailor shop windows: see a tailor's work, specialties, city and languages; save pieces you like |
| Orders from registered → in progress → fitting → delivered, with a reminder before each deadline and a calendar | "Ask about this": message the tailor about a specific piece; the design is pinned in the chat |
| Group orders for weddings and events, with per-member measurements | "Can you make this?": post a photo, a few words and an optional budget; tailors send offers (price or range + message); choose one and a conversation opens |
| Invoices & deposits: record a deposit, see the balance, share the invoice as a link or PDF | My measurements: keep your sizes in one place (type them or scan a sheet) and share them in a chat |
| Get found: publish finished work to Discover and keep a shop window (bio, city, specialties) | My orders: follow the status of what your tailor is making, add an order from the link your tailor sends |
| One shop link (seamflowtech.com/t/your-name) to share on WhatsApp, Instagram, printed cards | Messages: chat with your tailor, send photos, reply and react, see order cards in the thread |
| Requests board: see what clients near you are asking for and send an offer | Notifications when a tailor replies, sends an offer or updates your order |
| AI assistant by text or voice ("what is due this week?", "who owes me money?"), Design Studio moodboard, fabric library, PIN lock, works offline | Free to browse, no account needed to look |

Shared by both sides: in-app chat, orders both people can see, six app languages (the plan uses English + French), phone, tablet or browser.

## Don't promise these yet (not live)

Keep every post honest. These are on the roadmap but not in the product today, so no post, caption or ad should promise them:

| Not live yet | Say this instead (if needed) |
| --- | --- |
| Paying the tailor in the app (MTN MoMo / Orange Money) | Tailors can record deposits and share invoices. Don't mention in-app payment. |
| Reviews and star ratings | Talk about "real work by real tailors" and the Verified badge (granted by the SeamFlow team). |
| A "tailors near me" map | "Tailors in Douala" / "tailors in your city". |
| QR code to pass measurements to a new tailor | "Keep your measurements saved and share them in the chat." |
| Personal lookbook of everything made for you | Leave it out for now. |
| iPhone App Store app | Android + any browser (including on iPhone). |

Heads-up: the public website (seamflowtech.com) still speaks only to tailors. The two-audience version (tailor / customer toggle) is ready on the `feat/web-two-audience` branch. Deploy it before this plan starts sending clients to the site.

# 2. The big idea (positioning)

SeamFlow is where people who want clothes made for them meet the tailors who make them, and where the whole order, from the first photo to the final fitting, runs calmly in one place.

Campaign line: "Two sides, one thread." / "Deux côtés, un seul fil." (the same line the new website uses).

## One promise to each side

| To tailors & designers | To clients |
| --- | --- |
| "Get found for the work you already do, and run your whole workshop from your phone." "Faites-vous connaître grâce à votre travail, et gérez tout votre atelier depuis votre téléphone." | "Find a tailor you can trust, show what you want, and follow it until you wear it." "Trouvez un tailleur de confiance, montrez ce que vous voulez, et suivez-le jusqu'à ce que vous le portiez." |

## Why both sides need each other (and what that means for marketing)

SeamFlow grows in a loop: tailors publish real work → clients discover it and ask → tailors get new orders → tailors share their shop link and order links with the clients they already have → those clients join and bring friends.

- Tailors come first. A client who opens an empty feed leaves. So weeks 1–4 lean towards tailors, and the founding-tailor programme (section 8) fills Discover with real work before we push client content hard.

- Clients are the reason tailors stay. A tailor joins to get organised, but stays because SeamFlow brings them work. Client-facing content is what makes the tailor pitch believable.

- The best content is the tailors' own work. "Made on SeamFlow" posts (with permission) speak to both sides at once: clients see what they could get, tailors see what being featured looks like.

## The problem → the relief

### For tailors & designers

| The old way | With SeamFlow |
| --- | --- |
| "Where did I write Ama's measurements?" | Every client's measurements saved, even scanned from paper |
| Forgot the delivery date again | A reminder before every order is due |
| "Did they pay the deposit or not?" | See what's paid and what's left, on every order |
| New clients only by word of mouth | Your finished work shows in Discover; clients ask you directly |
| "Is it ready?" calls all day | Clients follow the order status themselves |
| Wedding orders on scattered paper | Group orders organised in one place |

### For clients

| The old way | With SeamFlow |
| --- | --- |
| "Who made your outfit? I need a good tailor." | Browse real work by real tailors in Douala |
| "I showed a photo and got something different." | Show the photo; the design stays pinned in the conversation |
| Giving your measurements again every time | Your measurements saved once, ready to share |
| Calling to ask "is my outfit ready?" | Follow your order from registered to delivered |
| Messages lost in a busy WhatsApp chat | One conversation with your tailor, with photos and the order |
| No idea who could make it, or for how much | Post "Can you make this?" and tailors send offers |

## The things to repeat (value points)

| Tailors & designers | Clients |
| --- | --- |
| Never lose a measurement again. | Find a tailor by their real work. |
| Never miss a deadline. | Show what you want, and let tailors come to you. |
| Always know who paid what. | Your measurements, saved and ready to share. |
| Get found by new clients. | Know where your outfit is, without calling. |
| Clients near you are asking: answer them. | Talk to your tailor in one place. |
| Look as professional as your work already is. | Free to browse. No account needed to look. |

# 3. Who we're talking to

Four people, one warm voice. Tag every post with who it is for (T = tailor, C = client, B = both) so the page stays balanced.

| Who | What they care about | How to speak to them |
| --- | --- | --- |
| T1 · The solo / home-based tailor | Beautiful work, drowning in admin; wants more clients without paying for ads | "You already do great work. We handle the messy part, and help people find you." |
| T2 · The growing atelier / fashion designer (styliste) | Staff, many clients, a brand to build; wants to look premium and be discovered | "Run your atelier like the fashion house it is, and show your collection to new clients." |
| C1 · The occasion dresser | Weddings, traditional ceremonies, church, graduations, end-of-year parties; wants it right and on time | "Show us the look. Find the tailor who can make it, and know it will be ready." |
| C2 · The client without a tailor (or who needs a new one) | New to Douala, back from abroad, or burned by a missed deadline; wants someone trustworthy | "Real work by real tailors. See before you choose." |

All four are mobile-first, active on Facebook, Instagram and especially WhatsApp, and speak French and/or English. Clients are style-conscious and follow fashion pages; tailors are proud of their craft. Both appreciate something that feels considered and premium, as long as it stays simple and obvious.

A note on words: say "tailor" and "fashion designer" in English, "tailleur", "couturier / couturière" and "styliste" in French. To clients, just say "you".

# 4. Voice & tone

Personality: warm, crafted, calm & confident, modern & clean. One voice, two registers: talk to tailors like a capable assistant who respects their craft; talk to clients like a friend who knows a great tailor.

## Do

- Start with the person's life and problem, then the app.

- Say who the post is for in the first words ("Tailors, …" / "Looking for a tailor?").

- Keep sentences short and plain. If a first-time user wouldn't understand it, rewrite it.

- Celebrate the craft. Tailors are the heroes of the client posts too.

- Always ask a tailor before featuring their work, and credit them by name.

- Post in English and French (see section 11).

## Don't

- No technical or startup words: "platform", "marketplace", "two-sided", "onboarding", "seamless solution".

- Never set clients and tailors against each other: no "cheap tailors", no haggling jokes, no "tailors who lie about dates".

- Never show a client's name, measurements or order details in content. The app itself never shows them in Discover; the page shouldn't either.

- Don't promise anything from the "not live yet" list in section 1.

- Don't crowd a flyer. One idea per image.

# 5. Brand kit for social

Updated to the current SeamFlow palette (the one in the app and in the three flyers already made). Hard rule unchanged: no pure black and no pure white; everything is warm-toned.

| Colour | Hex | Where to use it |
| --- | --- | --- |
| Warm cream (Linen) | #FAF7F2 | Main flyer background: friendly, light, welcoming |
| Brand purple | #7B30E8 | The "Flow" in the wordmark, highlighted headline words, the stitch bar |
| Deep violet | #5A18C9 | Headlines and buttons when you need more contrast |
| Copper | #D9673D | Warm accent; the audience label on client posts |
| Warm near-black (ink) | #1A1714 | Headlines and body text on light flyers (never #000000) |
| Muted ink | #5B554F | Supporting line under the headline |
| Midnight | #10101A | Background for dark flyers and app screenshots |
| Lavender | #C45BFF | Highlight words on dark flyers |
| Peach | #F2A66C | Warm accent on dark flyers |
| Warm off-white | #F2F0EB | Text on dark flyers (never #FFFFFF) |

## Telling the two audiences apart (without two brands)

One family, one look. The only difference is the small label above the headline (the "eyebrow"):

- Tailor posts: purple eyebrow, e.g. "FOR TAILORS · POUR LES TAILLEURS" or "THE EVERYDAY STRUGGLE".

- Client posts: copper eyebrow, e.g. "FOR YOU · POUR VOUS" or "LOOKING FOR A TAILOR?".

- Both: purple eyebrow "TWO SIDES, ONE THREAD · DEUX CÔTÉS, UN SEUL FIL".

If the website ships with its rose "customer" accent, keep copper on social anyway; it sits closer to the app, which now uses one theme for both sides.

## Fonts & logo

- Headlines: bold sans-serif (Inter Bold), as in the current flyers. Fraunces (elegant serif) is for statement and quote cards.

- Body: Inter. Numbers on screenshots: JetBrains Mono (optional). All free on Google Fonts.

- Logo: "Seam" in ink + "Flow" in purple, bottom-left on every flyer. Profile picture = the icon / app-icon logo.

- The one decoration: the short purple stitch bar under the headline. One per flyer, never as a divider.

# 6. Flyer design

## Principles (unchanged)

- One idea per flyer. Maximum ~12 words of text; the message must be clear in 2 seconds.

- Big headline, lots of warm empty space, logo in the same corner every time.

- Readable as a tiny thumbnail. Test it small before posting.

- Square 1080 × 1080 (feed) and portrait 1080 × 1350 (more reach on Instagram); stories 1080 × 1920. Keep text ~100 px from every edge.

## Templates

| Template | What it looks like | Use it for | For |
| --- | --- | --- | --- |
| A · Problem card | Cream or midnight bg, big headline (the pain), one line under, logo | Everyday struggle posts | T / C |
| B · Feature card | App screenshot + benefit headline + one line | Showing what SeamFlow does | T / C |
| C · Tip card | Cream bg, short numbered tip, stitch bar | Business tips (tailors), ordering & style tips (clients) | T / C |
| D · Statement card | One bold sentence centred, lots of space (Fraunces) | Big promises, quotes | B |
| E · Coming soon | Logo large, "Coming soon to Douala / Bientôt à Douala", follow prompt | Teasers | B |
| F · Made on SeamFlow (new) | A real finished piece full-bleed, tailor name + city in a soft overlay, small logo | Showcasing founding tailors | B |
| G · The loop carousel (new) | 5 slides: describe → tailors respond → agree → it gets made → delivered | Explaining how both sides fit | B |
| H · Side-by-side (new) | Split card: tailor screen left, client screen right, one shared headline | Showing the same order from both sides | B |

## The three flyers already made (docs/marketing-flyers)

- 01 "Your whole workshop, in one place." Still good. Use it as the first tailor feature post.

- 02 "Ever lost a client's measurements?" Still good. Use it as a tailor struggle post.

- 03 "Coming soon to Douala." Update the line "Something made for Douala's tailors is almost ready" to "Made for Douala's tailors, and the people they dress." / "Pour les tailleurs de Douala, et ceux qu'ils habillent."

# 7. Setting up the pages

## Names & handles

- Page name: SeamFlow · Handle: @seamflowtech on both Facebook and Instagram (fallbacks: @seamflow.app, @useseamflow, @seamflowapp; use the same one everywhere).

- Category: Facebook → "Software" or "Business Service"; Instagram → "Product/Service".

## Bio (bilingual, fits Instagram's 150 characters)

English: Where tailors & their clients meet 🧵 Find a tailor · Show what you want made · Run your workshop · Coming soon to Douala

Français : Tailleurs et clients, au même endroit 🧵 Trouvez un tailleur · Montrez ce que vous voulez · Gérez votre atelier · Bientôt à Douala

## Facebook "About" (longer)

SeamFlow brings tailors, fashion designers and their clients together. Clients discover real work by real tailors, ask "Can you make this?", keep their measurements in one place and follow their order to the final fitting. Tailors save every client and measurement, never miss a deadline, and get found for the work they already do. Coming soon to Douala. / SeamFlow réunit tailleurs, stylistes et clients. Les clients découvrent le vrai travail de vrais tailleurs, demandent « Pouvez-vous faire ceci ? », gardent leurs mesures au même endroit et suivent leur commande jusqu'au dernier essayage. Les tailleurs gardent chaque client et chaque mesure, ne ratent plus une date, et se font connaître grâce à leur travail. Bientôt à Douala.

## Profile, cover, link

- Profile picture: the icon / app-icon logo.

- Cover: the horizontal logo + "Two sides, one thread." on cream, with one tailor photo and one client photo on either side.

- Link: seamflowtech.com (deploy the two-audience version first; see section 1).

- Connect Facebook + Instagram in Meta Business Suite to post to both and answer all messages in one inbox.

## Story Highlights

"What is SeamFlow?" · "For tailors" · "For clients" · "How it works" · "Made on SeamFlow" · "Coming soon"

## Foundation posts (publish before anything else)

- Meet SeamFlow: "Two sides, one thread." Who it's for and the one-line promise to each side. (B)

- For tailors: "Get found. Stay organised." Flyer 01 works here. (T)

- For clients: "Find a tailor you can trust." (C)

- Coming soon: updated flyer 03. (B)

Instagram lets you pin three posts: pin 1, 2 and 3. On Facebook, pin "Meet SeamFlow".

# 8. Founding tailors (new: fill the feed before the clients arrive)

Client content only works if a client who taps through finds real work. So while the public page stays in "coming soon" mode, we quietly bring in a first group of Douala tailors and designers.

## The offer

- Name: "Founding tailors of SeamFlow" / "Tailleurs fondateurs de SeamFlow".

- They get: early access to the app, a "Made on SeamFlow" feature post on our page (a Collab post, so it shows on their profile too), priority when the team reviews tailors for the Verified badge, and a direct line to the team for feedback.

- They do: set up their shop window (bio, city, specialties, languages), publish 5–10 finished pieces to Discover, and share their shop link on their WhatsApp Status and Instagram.

- Do not promise free-forever pricing, payouts or ranking in the feed.

## How to find them

- Tailors you already know, and tailors whose work you see in Douala fashion groups and on Instagram.

- A DM or WhatsApp message first, never a public comment. Use the invitation text in section 16.

- Help each one set up in person or on a call. The first shop window is the hardest part.

## Suggested targets (adjust once you see the pace)

| By the end of | Founding tailors | Pieces published in Discover |
| --- | --- | --- |
| Week 3 | 10 | 50+ |
| Week 6 | 25 | 150+ |
| Week 8 (before ads) | 30+ | 200+, across women, men and children |

Bonus loop: every founding tailor who shares an order link with a client (a client can add that order to "My orders") brings a real client into SeamFlow before launch.

# 9. Content pillars (six buckets)

| Pillar | What it is | For | Share |
| --- | --- | --- | --- |
| 1. The everyday struggle | Relatable problems from both sides; makes people feel seen | T / C | 20% |
| 2. SeamFlow for tailors | Workshop features and "get found" features, shown as solutions | T | 20% |
| 3. SeamFlow for clients | Discover, "Can you make this?", measurements, order tracking, chat | C | 20% |
| 4. Made on SeamFlow | Founding tailors' real work, credited, with permission | B | 15% |
| 5. Tips | Business tips for tailors; ordering & style tips for clients | T / C | 15% |
| 6. Behind SeamFlow & community | The vision, coming-soon teasers, polls, "tag your tailor" | B | 10% |

Balance: weeks 1–4 run about 55% tailor / 45% client; weeks 5–8 flip to about 40% tailor / 60% client, once the feed has enough work behind it.

# 10. Content ideas by pillar

### Pillar 1: The everyday struggle

- (T) "Where did I write her measurements?" The lost notebook.

- (T) The delivery date you forgot until the client called.

- (T) "Did they pay the deposit… or not?"

- (C) "Who made your outfit?" Everyone asks; nobody has a name to give.

- (C) The photo you showed vs. what you got.

- (C) Calling three times to ask "is it ready?"

- (B) Wedding season: six matching outfits, one deadline, a lot of messages.

### Pillar 2: SeamFlow for tailors

- Every client's measurements saved, even scanned from a paper sheet (screen recording).

- Track an order from "registered" to "delivered", with a reminder before it is due.

- Show your finished work in Discover: new clients come to you.

- The Requests board: clients near you are asking "Can you make this?"

- One shop link for all your work: WhatsApp, Instagram, your business card.

- Ask the assistant: "What is due this week?" by voice while your hands are busy.

- Invoices and deposits: see what's paid and what's left.

### Pillar 3: SeamFlow for clients

- Discover: real work by real tailors, filtered by occasion.

- "Can you make this?" Post a photo, get offers, choose your tailor.

- "Ask about this": message a tailor about a piece you love.

- Your measurements, saved once, shared in a tap (or scanned from your tailor's sheet).

- Follow your order without calling.

- Browse for free, no account needed to look.

### Pillar 4: Made on SeamFlow

- Tailor spotlight: one founding tailor, three pieces, their city and specialties (carousel).

- "Occasion edit": five wedding looks by five SeamFlow tailors.

- From photo to fitting: a client's inspiration photo next to the finished piece (with both people's permission).

### Pillar 5: Tips

- (T) 3 ways to never lose a client's measurements.

- (T) How to take a deposit professionally, and keep track of it.

- (T) How to photograph your finished work so clients stop scrolling.

- (T) Getting organised before the busy season.

- (C) How to explain what you want to your tailor: photos, fabric, occasion, date.

- (C) How early to order for a wedding or ceremony.

- (C) What to bring to your first fitting.

### Pillar 6: Behind SeamFlow & community

- Founder note: "Why we're building SeamFlow for tailors and the people they dress."

- Poll: "How did you find your tailor?" (friend / social media / walked past / still looking).

- Poll: "Tailors, what's hardest: finding clients or keeping them organised?"

- "Tag your tailor" / "Tag the friend who always asks who made your outfit."

- "What would you want SeamFlow to do for you?"

# 11. Caption formula & bilingual format

## The 4-line formula (plus one rule)

Rule: say who the post is for in the first few words.

- Hook: a short, relatable line that stops the scroll.

- The problem: name the pain in one or two lines.

- The relief: how SeamFlow makes it easier.

- Soft call-to-action: follow / coming soon / tag / save.

## Both languages

Same as before; pick one and stay consistent: (a) English first, then French, in one caption, separated by a line and a flag; or (b) alternate the lead language, with a bilingual or neutral image.

## Example: tailor post

🇬🇧 Tailors, your best work deserves to be seen. Right now new clients only find you by word of mouth. On SeamFlow, your finished pieces show in Discover, and people can ask you to make one for them. 🧵 Coming soon to Douala. Follow along.

🇫🇷 Tailleurs, votre meilleur travail mérite d'être vu. Aujourd'hui, les nouveaux clients vous trouvent seulement par le bouche-à-oreille. Sur SeamFlow, vos pièces terminées apparaissent dans Découvrir, et on peut vous demander d'en réaliser une. 🧵 Bientôt à Douala. Suivez-nous.

## Example: client post

🇬🇧 Seen an outfit you love? Show it. No need to know a tailor first. Post the photo on SeamFlow, and tailors send you their offer. You choose. 🧵 Coming soon to Douala.

🇫🇷 Vous avez vu une tenue qui vous plaît ? Montrez-la. Pas besoin de connaître un tailleur. Publiez la photo sur SeamFlow, et les tailleurs vous envoient leur offre. C'est vous qui choisissez. 🧵 Bientôt à Douala.

## Soft CTAs to rotate

- "Follow so you don't miss the launch." / "Suivez-nous pour ne pas manquer le lancement."

- "Coming soon to Douala." / "Bientôt à Douala."

- "Tag your tailor." / "Identifiez votre tailleur."

- "Tag the friend who always asks who made your outfit." / "Identifiez l'ami(e) qui demande toujours qui a fait votre tenue."

- "Tailors: want to be one of the first in Douala? Send us a message." / "Tailleurs : vous voulez faire partie des premiers à Douala ? Écrivez-nous."

- "Save this for later." / "Enregistrez pour plus tard."

# 12. Posting calendar: 2 months

## Rhythm

- 4 feed posts a week: Monday, Wednesday, Friday, Saturday.

- 3–5 stories a week; alternate tailor and client stories (polls, questions, behind the scenes, re-shares of founding tailors' posts).

- Best times (WAT): around 12–1 pm and 7–9 pm; 6–8 am also works. Saturday evenings suit client and occasion content.

- Carousels and portrait 1080×1350 get the most reach: use them for features, tips and showcases.

## The 8-week plan

Weeks 1–2: awareness, who we are for both sides. Weeks 3–4: tailor recruitment + first showcases. Weeks 5–6: client value, backed by real work. Weeks 7–8: how it all fits + anticipation. (T/C/B = audience, P = pillar.)

| # | Monday | Wednesday | Friday | Saturday |
| --- | --- | --- | --- | --- |
| 1 | Meet SeamFlow: two sides, one thread (B·P6) | Lost the measurements notebook: flyer 02 (T·P1) | "Who made your outfit?" (C·P1) | Poll: how did you find your tailor? (B·P6) |
| 2 | Your workshop in one place: flyer 01 (T·P2) | Discover real work by real tailors (C·P3) | Tip: 3 ways to never lose measurements (T·P5) | "Is my outfit ready?" (B·P1) |
| 3 | Get found: show your work in Discover (T·P2) | Founding tailors wanted (T·P6) | Tip: how to explain what you want (C·P5) | Made on SeamFlow #1 (B·P4) |
| 4 | "Can you make this?" (C·P3) | Clients near you are asking: Requests (T·P2) | Wedding season chaos (B·P1) | Tag your tailor (B·P6) |
| 5 | Your measurements, saved and ready (C·P3) | Tip: take a deposit professionally (T·P5) | Made on SeamFlow #2: occasion edit (B·P4) | Poll: hardest part of ordering made-to-measure? (C·P6) |
| 6 | Follow your order without calling (C·P3) | Ask the assistant, by voice (T·P2) | The photo vs. what I got (C·P1) | Founder note: why both sides (B·P6) |
| 7 | How it works: loop carousel (B·P2/3) | Tip: what to bring to a fitting (C·P5) | One shop link for all your work (T·P2) | Tailor spotlight #3 (B·P4) |
| 8 | Same order, both sides: side-by-side (B·P2/3) | Tip: get your atelier ready for the busy season (T·P5) | Launching soon: follow so you don't miss it (B·P6) | What do you want most? + recap (B·P6) |

Reusable weekly template after week 8: Mon = client feature · Wed = tailor feature or tip · Fri = Made on SeamFlow or struggle · Sat = community.

# 13. Hashtags & keywords

Instagram: about 10–15 tags per post (branded + one full set + a few from another). Facebook: 3–5. Pick sets that match the post's audience.

Always use (branded): #SeamFlow #SeamFlowApp #MadeOnSeamFlow #237

| Set | Hashtags | Best for |
| --- | --- | --- |
| A · Tailoring & craft | #TailorLife #Couturier #Couture237 #TailorsOfCameroon #FashionDesigner #Styliste #Bespoke #SewingBusiness #AtelierLife #ModeCamerounaise | T |
| B · Cameroon & local | #CameroonFashion #237Fashion #DoualaFashion #YaoundeFashion #MadeInCameroon #Cameroun #Douala #Mboa #CameroonBusiness | B |
| C · African fashion | #AfricanFashion #Ankara #AnkaraStyles #AfricanPrint #Kaba #Agbada #AfricanDesigner #FashionAfrica #PagneAfricain #StyleAfricain | B |
| D · Business & tips | #SmallBusiness237 #TailoringBusiness #FashionEntrepreneur #BusinessTips #GestionAtelier #Entrepreneuriat #PME237 #GrowYourBusiness | T |
| E · Client & style (new) | #SurMesure #MadeToMeasure #CustomMade #TenueDuJour #OOTD237 #MariageCamerounais #WeddingGuest #TenueTraditionnelle #StyleCamerounais #ModeDouala | C |

Keywords for bios, captions and "About": tailor app, find a tailor, tailor in Douala, made to measure, wedding outfit, client measurements, order tracking, atelier, couturier, styliste, trouver un couturier, tailleur à Douala, sur mesure, tenue de mariage, mesures, suivi de commande.

# 14. Growing the page (no budget, before ads)

## Both sides

- WhatsApp Status is still the secret weapon. Post every flyer there too, and ask friends to re-share.

- Reply to every comment and DM within a day, warmly. Answer tailors and clients in the language they wrote in.

- Weekly story polls and questions: they tell you what each side wants, and keep the page active.

- Cross-post Facebook ↔ Instagram from Meta Business Suite.

## Reaching tailors

- Founding tailors (section 8) are the main channel: every Collab post puts SeamFlow in front of their followers, who are future clients.

- Share tailor posts in Cameroon fashion and tailoring Facebook groups (where allowed).

- Comment on and support local tailors' posts. Be a helpful presence, not a spammer.

## Reaching clients

- Founding tailors' own clients: when a tailor shares their shop link or an order link, their clients meet SeamFlow through someone they already trust.

- Engage with Douala wedding, event and style pages, and "who made your outfit?" conversations. Credit the tailor, don't sell.

- Invite a few Douala style creators to repost a "Made on SeamFlow" piece they like (no paid deals in this phase).

- Occasion moments: weddings, end-of-year parties, back-to-school uniforms, Christmas and New Year outfits. Plan occasion edits two to three weeks ahead.

# 15. Getting ready for the video ads

Before switching on video ads, the page and the product should have:

- At least 12 quality posts, with both tailor and client content visible in the first nine tiles of the grid.

- Bilingual bio, logo profile picture, two-sided cover, all six Story Highlights.

- The three foundation posts pinned (Meet SeamFlow, For tailors, For clients).

- Enough real work in Discover (target: 30+ founding tailors, 200+ pieces), so a client who taps through never sees an empty feed.

- The two-audience website live on seamflowtech.com.

## Plan two ad tracks, not one

|  | Tailor track | Client track |
| --- | --- | --- |
| Audience | Tailoring, sewing, fashion design, small business interests; Douala | Fashion, weddings, African fashion, events; Douala |
| Video idea | "A day in the workshop": notebook chaos → the same day on SeamFlow | "From photo to fitting": a screenshot of a look → offers → the finished piece |
| Message | Get found. Stay organised. | Find your tailor. Get what you actually want. |
| Lands on | Tailor view of the website / Pinned "For tailors" post | Customer view of the website / Pinned "For clients" post |

Why this matters: each ad sends people to the page. If they see content made for them and a feed full of real work, they follow and remember you. If they see content for someone else, or an empty feed, the money is wasted.

# 16. What to watch (keep it simple)

Check once a week. Track each number separately for tailor posts and client posts (use the T / C / B tag).

| Metric | Why it matters |
| --- | --- |
| Saves & shares | The best sign content is useful. Tips and struggle posts usually lead. |
| Follower growth | A steady climb week over week. |
| Reach & profile visits | How many new people you touch on each side. |
| Comments & DMs: from tailors vs. from clients | Real interest, and a quick read of the balance between the sides. |
| Founding tailors signed up | Supply: the thing client content depends on. |
| Pieces published in Discover | Whether the feed is full enough to send clients to. |

Balance rule: if client interest grows faster than tailors join, shift the next two weeks towards tailor recruitment and showcases. If tailors join but client posts stay quiet, add more occasion edits and client tips.

# 17. Your first 14 days (checklist)

- Deploy the two-audience website (or at least review it) before linking to it.

- Create the Facebook Page and Instagram Business account with the same handle; connect them in Meta Business Suite.

- Set the profile picture, the two-sided cover and the new bilingual bio.

- Create the six Story Highlights.

- Update flyer 03 with the new line; design the "For clients" foundation flyer.

- Publish the four foundation posts; pin Meet SeamFlow, For tailors and For clients.

- Send the founding-tailor invitation to your first 15–20 tailors; help the first five set up their shop window.

- Follow the Week 1 and Week 2 calendar: Mon, Wed, Fri, Sat.

- Post every flyer to WhatsApp Status too.

- Reply to every comment and DM within a day; note whether each came from a tailor or a client.

# 18. Ready-to-post copy bank

Pair each caption with a simple flyer. EN + FR.

## For tailors

### T1 · Never lose a measurement again.

EN: That notebook full of measurements? Imagine it never getting lost. SeamFlow keeps every client's sizes safe, and can even read them from a paper sheet. 🧵 Coming soon to Douala.

FR : Ce carnet plein de mesures ? Imaginez ne plus jamais le perdre. SeamFlow garde les mesures de chaque client, et peut même les lire sur une fiche papier. 🧵 Bientôt à Douala.

### T2 · Get found for your work.

EN: Tailors, your finished pieces are your best advert. On SeamFlow they show in Discover, where clients can ask you to make one for them. Follow along. 🧵

FR : Tailleurs, vos pièces terminées sont votre meilleure publicité. Sur SeamFlow, elles apparaissent dans Découvrir, où les clients peuvent vous demander d'en réaliser une. Suivez-nous. 🧵

### T3 · Clients are asking.

EN: "Can you make this?" On SeamFlow, clients post a photo of what they want and tailors send an offer. A good reply is enough; no big portfolio needed. 🧵 Coming soon to Douala.

FR : « Pouvez-vous faire ceci ? » Sur SeamFlow, les clients publient la photo de ce qu'ils veulent et les tailleurs envoient une offre. Une bonne réponse suffit, pas besoin d'un grand portfolio. 🧵 Bientôt à Douala.

### T4 · Never miss a delivery date.

EN: No more "is it ready?" surprises. SeamFlow reminds you before every order is due, and your client can follow the progress too. 🧵

FR : Fini les surprises du « c'est prêt ? ». SeamFlow vous rappelle chaque échéance, et votre client peut suivre l'avancement lui aussi. 🧵

## For clients

### C1 · Find a tailor by their work.

EN: Looking for a tailor? See their real work first. SeamFlow shows finished pieces by tailors in Douala, for weddings, ceremonies, work and more. 🧵 Coming soon.

FR : Vous cherchez un tailleur ? Voyez d'abord son vrai travail. SeamFlow montre les pièces réalisées par des tailleurs de Douala, pour les mariages, les cérémonies, le travail et plus encore. 🧵 Bientôt.

### C2 · Show what you want made.

EN: Saw a look you love? Post the photo, add a few words and your budget if you like, and tailors send you their offer. You choose. 🧵 Coming soon to Douala.

FR : Vous avez vu une tenue qui vous plaît ? Publiez la photo, ajoutez quelques mots et votre budget si vous voulez, et les tailleurs vous envoient leur offre. C'est vous qui choisissez. 🧵 Bientôt à Douala.

### C3 · Your measurements, in your pocket.

EN: Tired of being measured from scratch? Keep your measurements on SeamFlow and share them with your tailor in a tap. 🧵 Save this for later.

FR : Marre de reprendre vos mesures à zéro ? Gardez-les sur SeamFlow et partagez-les avec votre tailleur en un geste. 🧵 Enregistrez pour plus tard.

### C4 · Know where your outfit is.

EN: No more calling to ask "is it ready?" Follow your order from the first cut to the final fitting, and message your tailor in one place. 🧵 Tag your tailor.

FR : Plus besoin d'appeler pour demander « c'est prêt ? ». Suivez votre commande de la première coupe au dernier essayage, et écrivez à votre tailleur au même endroit. 🧵 Identifiez votre tailleur.

## For both

### B1 · Two sides, one thread.

EN: You know what you want to wear. They know how to make it. SeamFlow brings you together, and keeps the whole order calm, from the first photo to the final fitting. 🧵 Coming soon to Douala.

FR : Vous savez ce que vous voulez porter. Ils savent comment le réaliser. SeamFlow vous réunit, et garde toute la commande sereine, de la première photo au dernier essayage. 🧵 Bientôt à Douala.

### B2 · Made on SeamFlow (showcase template).

EN: Made by [Tailor name], [City] ✂️ [One line about the piece]. Real work by real tailors, soon on SeamFlow. 🧵 Tag someone who needs this look.

FR : Réalisé par [Nom du tailleur], [Ville] ✂️ [Une ligne sur la pièce]. Le vrai travail de vrais tailleurs, bientôt sur SeamFlow. 🧵 Identifiez quelqu'un à qui ce style irait bien.

## Founding-tailor invitation (DM / WhatsApp)

EN: Hello [Name], I love your work, especially [piece]. We're building SeamFlow, an app where tailors in Douala organise their clients and orders, and where clients find tailors through their real work. We're inviting a small group of founding tailors to try it before launch and be featured on our page. Could I show you in 10 minutes?

FR : Bonjour [Nom], j'aime beaucoup votre travail, surtout [pièce]. Nous créons SeamFlow, une appli où les tailleurs de Douala organisent leurs clients et leurs commandes, et où les clients trouvent un tailleur grâce à son vrai travail. Nous invitons un petit groupe de tailleurs fondateurs à l'essayer avant le lancement et à être mis en avant sur notre page. Je peux vous la montrer en 10 minutes ?

## Taglines to reuse

- "Two sides, one thread." / "Deux côtés, un seul fil."

- "Where tailors and the people they dress meet." / "Là où les tailleurs rencontrent ceux qu'ils habillent."

- "Find your tailor. Get what you actually want." / "Trouvez votre tailleur. Obtenez ce que vous voulez vraiment."

- "Get found. Stay organised." / "Faites-vous connaître. Restez organisé."

- "Your whole workshop, in one place." / "Tout votre atelier, au même endroit."